## Sheet1
Date	Start time	End time	Duration	Work		TOTAL TIME:	125:30:00
24.4.2013	10:30:00	12:45:00	02:15:00	Initial setup, start of Introduction, etc.
28.4.2013	16:00:00	18:00:00	02:00:00	First mockup, header/footer, bit of text
2.5.2013	17:00:00	17:30:00	00:30:00	Reformatting
10.5.2013	18:00:00	20:00:00	02:00:00	Application and general progress
12.5.2013	19:00:00	20:00:00	01:00:00	Sequence diagram, framework things
15.5.2013	16:30:00	17:15:00	00:45:00	Small stuff (lots of todos :P )
16.5.2013	17:00:00	18:00:00	01:00:00	Dialog structure, etc
18.5.2013	13:00:00	13:30:00	00:30:00	Small work
19.5.2013	15:45:00	16:15:00	00:30:00	Started Class Diagramm
20.5.2013	13:30:00	14:45:00	01:15:00	Framework stuff
24.5.2013	13:00:00	15:00:00	02:00:00	Adapted styleguide
30.5.2013	15:00:00	16:00:00	01:00:00	Small things (also stuff from first talk)
5.6.2013	23:00:00	00:00:00	01:00:00	More Mockups... lots of preparatory work around them too
7.6.2013	15:30:00	16:15:00	00:45:00	Marker Mockups
9.6.2013	14:00:00	16:20:00	02:20:00	Finished mockups, corrected tasks, some small things; Prepared implementation
12.6.2013	16:30:00	17:45:00	01:15:00	Started app layout
13.6.2013	15:30:00	17:00:00	01:30:00	Switched from sh** eclipse to intellij, finalized layout, started reading into camera
20.6.2013	15:30:00	17:20:00	01:50:00	Menu layout. Android layout sucks!!!
14.7.2013	14:00:00	16:30:00	02:30:00	reading
18.7.2013	15:00:00	19:00:00	04:00:00	OpenCV Code testing and reading
7.8.2013	15:00:00	17:30:00	02:30:00	Finally got feature detection to work!
9.8.2013	17:00:00	19:00:00	02:00:00	Feature matching started.
10.8.2013	14:00:00	15:00:00	01:00:00	Discovered Aruco for Android, Performance testing of feature tracking
24.8.2013	12:30:00	14:30:00	02:00:00	Scratch feature, got polymaker started & working ()
24.8.2013	16:00:00	16:50:00	00:50:00	Updated some of the thesis to account for the new approach to detect markers
26.8.2013	15:00:00	17:00:00	02:00:00	Tried some optimizations
30.8.2013	15:00:00	17:45:00	02:45:00	Tried multithreading, optimizations
31.8.2013	14:00:00	15:00:00	01:00:00	Tried aruco, updated some doc.
2.9.2013	14:00:00	17:00:00	03:00:00	Implemented working multithreading, read up on next steps
5.9.2013	13:30:00	16:45:00	03:15:00	Started work on perspective transformation
6.9.2013	14:00:00	17:00:00	03:00:00	Got perspective transformation to work! :D
7.9.2013	14:00:00	17:00:00	03:00:00	Started marker ID
8.9.2013	12:00:00	16:30:00	04:30:00	Continue marker ID
9.9.2013	14:00:00	17:00:00	03:00:00	Started final repo, made everything work, final ID still missing
12.9.2013	18:00:00	18:30:00	00:30:00	Read OpenGL Android stuff
15.9.2013	13:00:00	18:00:00	05:00:00	Mainly restructuring to final form, started OpenGL implementation basics
16.9.2013	14:30:00	18:00:00	03:30:00	Simplified attachment of view, opengl now rendering as overlay
17.9.2013	12:30:00	19:00:00	06:30:00	Implemented ID with hamming code, finished marker detection
18.9.2013	13:30:00	16:20:00	02:50:00	Finished prework for OpenGL stuff, started rendering objects (not working yet)
18.9.2013	17:00:00	17:45:00	00:45:00	Updated some of the docu, added new marker chapter
19.9.2013	23:00:00	23:15:00	00:15:00	Small text, mainly correction for how markers are detected in framework implementation
20.9.2013	23:00:00	23:15:00	00:15:00	Checked docu, added todos, removed wrong things, general update
21.9.2013	13:30:00	14:45:00	01:15:00	Working on performance optimizations in Detector, also killing bugs
21.9.2013	16:00:00	17:30:00	01:30:00	Trying to kill the Opengl bug day 1 :P
22.9.2013	12:45:00	16:15:00	03:30:00	Killed OpenGL bug! Improved lots too. Realized I'll need correct pose estimization
23.9.2013	13:00:00	16:30:00	03:30:00	Pose estimization in and working correctly, I think – now I only need to apply it!
25.9.2013	13:30:00	16:40:00	03:10:00	Docu update, mainly framework and reformatting
27.9.2013	23:30:00	00:00:00	00:30:00	Small work on results
28.8.2013	16:15:00	17:30:00	01:15:00	Correct 3D rendering on top of marker now works, with bugs though! WOHOO!
29.9.2013	13:45:00	14:30:00	00:45:00	Corrected translation matrix flickering
29.9.2013	17:30:00	19:00:00	01:30:00	Documentation: difficulties first complete version, started performance
30.9.2013	12:30:00	14:00:00	01:30:00	Did performance analysis (experiment), finished first performance text
01.10.2013	22:00:00	22:30:00	00:30:00	Further text, corrected some citations
02.10.2013	20:45:00	21:30:00	00:45:00	Finished draft capabilites, started layout of conclusion: still missing comparison to aruco
3.10.2013	18:00:00	19:00:00	01:00:00	Drafted conclusion. Glossary and gratitude still missing.
4.10.2013	16:00:00	18:00:00	02:00:00	Comparison done. Small further work, almost done! :D
5.10.2013	14:15:00	18:30:00	04:15:00	First draft done! YES! :D Also started visibilty correction in framework.
6.10.2013	14:00:00	17:00:00	03:00:00	V1.1 done! Sent to supervisor
7.10.2013	15:45:00	16:15:00	00:30:00	Removed application section, now in results as evaluating app
7.10.2013	17:00:00	18:30:00	01:30:00	Implemented double removal of double contour detection
8.10.2013	13:30:00	16:45:00	03:15:00	First correction. V1.2
9.10.2013	10:00:00	10:30:00	00:30:00	Meeting Marc
9.10.2013	16:00:00	16:30:00	00:30:00	next correction – V1.3. Now only missing application
10.10.2013	14:00:00	17:30:00	03:30:00	Tried multi activity stuff, not working yet, instead implemented features and removed bugs
11.10.2013	13:30:00	16:00:00	02:30:00	Multiply activites now working, added menu.
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00
			00:00:00